## Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (1,2,3,5) | Priority | Risk | Assignee(s) | Due Date | Completed | Sprint
17 | US-01 As a user I want to be greeted by a home page | As a user, I want to be greeted by a home page with an intuitive UI and easy navigation that links to all of the important pages of the website. | 1 | Low | Low | Shadi, Scott |  | Yes | 1
18 | TSK-01 Create a "contact us" page | Help page will be accessed from the footer and provides a form that allows the user to contact customer service. | 1 | Low | Low | Shadi, Scott |  | Yes | 1
19 | TSK-02 Create a privacy policy page | The page is accessible from the footer and contains the privacy policy that applies to the website features. | 1 | Low | Low | Shadi |  | Yes | 1
20 | TSK-03 Add button the links to login page | The button has to be in the navbar and it must link to the account creation page. | 1 | High | Med | Shadi |  | Yes | 1
21 | TSK-04 Create a terms and conditions page | The page will accessible from the footer. | 1 | Low | Low | Shadi |  | Yes | 1
22 | TSK-05 Add a sign up button | Add the sign up button in the navbar to create a new user/admin account. | 1 | High | Med | Shadi |  | Yes | 1
23 | US-02 As an user I want to create an user/admin account | As a user, I want to have the option between creating an user or an admin account by selecting it from a specific button. | 3 | High | High | Kalin, Vanessa |  | Yes | 1
26 | TSK-08 Store the account data into the database (POST) | This stores the account data for user and admin accounts. | 3 | High | High | Kalin, Vanessa |  | Yes | 1
27 | US-03 As an user or admin I want to have the option to login into my existing account | As a user, I want to have the option between login as an user or an admin by selecting it from a specific button. | 4 | High | Med | Shadi, Kalin, Scott |  | Yes | 1
28 | TSK-09 Create the login form | The login form requires: User name Password | 2 | High | High | Shadi |  | Yes | 1
29 | TSK-010 Login authentication | Verify the the provided username and password match the database. Warning message shown if credentials are invalid. | 4 | High | High | Kalin |  | Yes | 1
30 | TSK-011 Users with valid credentials are redirected to their dashboard | Users with valid credentials are redirected to their dashboard. | 1 | Med | Low | Kalin |  | Yes | 1
31 | TSK-012 Create user or admin login button | The login page includes two buttons for user or admin login that display the relative login forms. | 2 | High | High | Shadi |  | Yes | 1
32 | US-04 As an admin I want to create teams | As an admin, I want the ability to create new teams by clicking a button on the left sidebar. | 3 | High | High | Andy |  | Yes | 1
33 | TSK-013 Create a button to create a new team | The button is going to be on the left-side bar allowing the admin to create a new team. | 2 | High | High | Andy |  | Yes | 1
34 | TSK-014 Create a team creation form | The creation form will require: Team name Description | 3 | High | High | Andy |  | Yes | 1
25 | TSK-07 Create admin signup form | The sign up form requires: First name, Last name, User name, Email, Country, Password, Confirm Password | 2 | High | High | Shadi |  | Yes | 1
44 | TSK-016 Create team page | The team page is where the admin can add channels to the team and all existing team channels are visible. | 3 | High | High | Andy |  | Yes
35 | US-05 As an admin I want to be able to add users to a team | As a admin, I want the ability to add any number of users into a team. | 3 | Med | Med | Weitao, Andy |  | Yes | 1
36 | TSK-017 Create a button to add member | The button to add members will appear in the team page. Clicking the button takes the admin to a form where he can select among the available users. | 2 | Med | Med | Andy |  | Yes | 1
37 | TSK-018 Create the add users form | The form will contain a list of all available usernames to be added. The forms includes a button to add the selected users. | 3 | High | High | Andy |  | Yes | 1
43 | TSK-019 Add user data to team's database (PATCH) | The users' usernames are added to the team's database through a PATCH method. | 4 | High | High | Kalin, Vanessa |  | Yes | 1
38 | US-06 As an admin I want to be able to create a channel | As a admin, I want the ability to create new channels by clicking a button in the team page. | 3 | High | High | Vanessa, Andy |  | Yes | 1
39 | TSK-020 Create add channel button | The button is in the team page and leads the admin the channel creation form. | 2 | Med | Med | Scott |  | Yes | 1
40 | TSK-021 Create channel creation form | The channel creation form requires the name of the channel. The form includes a button that creates the channel. | 2 | Med | Med | Scott |  | Yes | 1
42 | TSK-022 Add the channel data to the database (POST) | The channel's name will be added to the channel's database through a POST method. | 3 | High | High | Vanessa |  | No | 1
41 | TSK-015 Add the team data into the database (POST) | The team name and description are added to the channels database through a POST method. | 3 | High | High | Kalin |  | No | 1
45 | US-07 As an admin, I want to be able to add team members to a channel | As an admin, I want the ability to add any number of team members to a team channel. | 4 | High | High | Kalin |  | Yes | 1
46 | TSK-024 Create button to add users into channel | The button is the channel's page | 2 | High | Low | Scott |  | Yes | 2
47 | TSK-023 Create channel page | The channel page is where the admin can add users to the channel and all existing channels members are visible. | 3 | Med | Med | Vanessa |  | No | 2
49 | TSK-025 Create add users to channel form | The add users to channels form allows the admin to select the usernames they wish to add which are available from the team's database. | 3 | High | Med | Vanessa |  | Yes | 2
50 | TSK-026 Add the users' data to the channel's database (PATCH) | The usernames of the added users are added to the channels database through a PATCH method. | 4 | High | High | Kalin |  | Yes | 1
54 | TSK-027 Create user dashboard | Create the dashboard that the user is redirected to after login | 3 | Med | Med | Scott, Shadi |  | Yes | 2
67 | TSK-028 Create admin dashboard | Dashboard from which an admin can create teams, channels and add users to teams and channels. | 3 | High | Med | Shadi, Scott, Andy |  | Yes | 1

## Sprint 2
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (1,2,3,5) | Priority | Risk | Assignee(s) | Due Date | Completed | Sprint
73 | US-011 As a user I want direct message conversations to remain private so that no one else can access them | As a user I want direct message conversations to remain private so that only the participants can view and access them securely | 4 | High | High | Andy, Kalin, Vanessa, Shadi | 30/02/2025 | Yes | 2
72 | US-010 As a user I want to send direct messages to other users so that I can have private conversations | As a user I want to send direct messages to other users so that I can have private one on one communication | 4 | High | High | Kalin, Vanessa, Shadi | 28/02/2025 | Yes | 2
71 | US-009 As an admin I want to moderate messages in a channel so that I can remove inappropriate ones | As an admin I want to moderate messages in a channel so that I can delete inappropriate or irrelevant messages to maintain a healthy communication environment | 4 | High | Low | Andy | 17/02/2025 | Yes | 2
70 | US-008 As a user I want to send messages in a text channel so that all users in the channel can see them | As a user I want to send messages in a text channel so that I can communicate with all members of the channel in real time. | 4 | High | High | Shadi | 17/02/2025 | Yes | 2
54 | TSK-27 Create user dashboard | create the dashboard that the user is redirected to after login | 2 | Low | Low | Shadi | 2025-12-02 | Yes | 2
49 | TSK-025 Create add users to channel form | The add users to channels form allows the admin to select the usernames he wishes to add which are available from the team's database. | 2 | Med | High | Scott | 2025-02-03 | Yes | 2
47 | TSK-023 Create channel page | The channel page is where the admin can add users to the channel and all existing channels members are visible. | 2 | Med | High | Scott, Shadi | 2025-02-03 | Yes | 2
90 | TSK-041 Add UI indicators to show that conversations are private and secure | Add UI indicators to show that conversations are private and secure. | 1 | Low | Low | Scott | 28/02/2025 | Yes | 2
89 | TSK-040 Implement security measures such as encryption to protect message data | Implement security measures such as encryption to protect message data | 5 | High | High | Kalin, Vanessa | 28/02/2025 | Yes | 2
88 | TSK-039 Add backend logic to restrict message visibility to participants only | Add backend logic to restrict message visibility to participants only, this might have to include a "participants" or "sender" and "receiver" attributes in the db table. | 3 | Med | Med | Kalin | 2025-01-02 | Yes | 2
87 | TSK-038 Store direct messages in the database with relevant information | Create database for storing private messages. Store direct messages in the database with timestamps, usernames and message content through POST method. | 3 | Med | Med | Vanessa | 29/02/2025 | Yes | 2
86 | TSK-037 Implement backend functionality for receiving messages | Implement backend functionality for receiving messages through a GET method | 4 | High | High | Kalin, Vanessa, Weitao | 30/02/2025 | Yes | 2
85 | TSK-036 Implement backend functionality for sending messages | Implement backend functionality for sending messages through POST method. | 4 | High | High | Shadi, Kalin, Vanessa, Andy, Scott, Weitao | 20/02/2025 | Yes | 2
83 | TSK-034 Implement functionality to delete messages from the database and UI | Implement functionality to delete messages from the database and UI through a DELETE method | 4 | High | High | Andy, Kalin, Vanessa | 2025-01-02 | Yes | 2
81 | TSK-032 Implement functionality display messages in real time | The messages are displayed on the UI through a POST method | 5 | High | High | Shadi, Kalin, Vanessa, Andy | 28/02/2025 | Yes | 2
80 | TSK-031 Implement functionality to send messages in real time | The messages are sent by clicking a "send" button | 5 | High | High | Shadi, Kalin, Vanessa, Andy | 28/02/2025 | Yes | 2
79 | TSK-030 Store messages in the database with timestamps and user information | Create database table with timestamps, username and content (message itself) attributes and POST the message info into the database | 4 | Med | Med | Andy, Vanessa, Kalin | 30/02/2025 | Yes | 2

## Sprint 3
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (1,2,3,5) | Priority | Risk | Assignee(s) | Due Date | Completed | Sprint
110 | US-012 As a user, I want to create private channels and invite members to them | As a User, I want to create private channels and invite existing team members to them | 4 | Med | High | Kalin | 21/03/2025 | Yes | 3
111 | TSK-042 Add a private channel creation button for users | Add a private channel creation button for users. | 1 | Med | Low | Kalin | 21/03/2025 | Yes | 3
112 | TSK-043 Create an invite pop-up | Create an invite pop-up to send out invitations to users | 2 | Med | Med | Kalin | 21/03/2025 | Yes | 3
113 | TSK-044 Send invitation to users via direct messaging | Invited user will receive a direct message from the channel creator to accept or decline an invitation. | 4 | High | High | Kalin | 21/03/2025 | Yes | 3
114 | TSK-045 Add users to the channel's database | Users that accept the invitation will be added to the channel's database. | 3 | High | High | Kalin | 21/03/2025 | Yes | 3
115 | TSK-046 Make channel messages visible to channel members only | Channel messages will be visible to channel members only. | 2 | Med | Low | Kalin | 21/03/2025 | Yes | 3
116 | US-013 As a user, I want to able to request to join channels and leave them | As a user, I want to able request to join private channels by sending a request to the channel creator and also to leave private channels. | 3 | Med | Med | Vanessa | 21/03/2025 | Yes | 3
117 | TSK-059 Add a button to request channel membership | The button is on the channel page if the user is not a member of the channel. The request sends a direct message to the channel owner. | 3 | High | High | Vanessa | 21/03/2025 | Yes | 3
118 | TSK-048 Add a button to leave private channel | The button will be visible on the channel page for channel members. | 1 | Med | Low | Vanessa | 21/03/2025 | Yes | 3
119 | TSK-049 Remove users from channel database | Users that select the "leave" button will be removed from the database. | 1 | Med | Low | Vanessa | 21/03/2025 | Yes | 3
120 | US-014 As a user/admin, I want to have more information on other registered members | As a logged in member, I want to have more information on the status and presence of other registered members. | 2 | Low | Low | Shadi | 21/03/2025 | Yes | 3
121 | TSK-047 Add a list of registered users on the dashboard | Add a list of all registered users on the admin/user dashboard. | 3 | Med | High | Shadi | 21/03/2025 | Yes | 3
122 | TSK-060 Add a status indicator to the registered users list | The indicator will include "online", "offline" and "away" status | 3 | Med | High | Scott | 21/03/2025 | Yes | 3
123 | TSK-049 Add a drop-down menu where users can select their status. | The drop-down menu will show up when hovering over the profile picture. | 2 | Low | Med | Scott | 21/03/2025 | Yes | 3
125 | TSK-050 Add status attribute the member's database | Add status attribute the member's database. | 1 | High | Low | Kalin | 21/03/2025 | Yes | 3
126 | TSK-051 Add a "last seen" timestamp to each user | Add a "last seen" timestamp to the registered users list for each user in EST time. | 3 | Med | Low | Vanessa, Kalin | 21/03/2025 | Yes | 3
130 | TSK-052 Add functionality to send direct messages to offline members | Add functionality to send direct messages to offline members. | 2 | High | Med | Vanessa, Kalin | 21/03/2025 | Yes | 3
124 | US-015 As a user I want to have emoji support in messages so that I can express myself effectively | As a user I want to send messages with emoji support so that I can enhance my communication with visual expressions | 3 | Med | High | Vanessa, Andy, Kalin | 21/03/2025 | Yes | 3
127 | TSK-053 Add an emoji picker to the message input field | Add an emoji picker to the message input field | 2 | Med | Low | Andy | 21/03/2025 | Yes | 3
128 | TSK-054 Store emoji messages correctly in the database | Store emoji messages correctly in the database | 2 | Med | High | Vanessa | 21/03/2025 | Yes | 3
129 | TSK-055 Ensure emojis appear properly in the chat interface | Ensure emojis appear properly in the chat interface | 2 | Med | Low | Andy, Shadi | 21/03/2025 | Yes | 3
131 | US-016 As a user I want to reply to messages with quoting so that I can reference previous messages | As a user I want to reply to messages with quoting so that I can refer to specific messages in conversations | 3 | Med | Med | Andy | 21/03/2025 | Yes | 3
132 | TSK-055 Add a "Reply" button to each message | Add a "Reply" button to each message | 1 | Med | High | Andy | 21/03/2025 | Yes | 3
133 | TSK-056 Implement functionality to attach the quoted message to the new reply | Implement functionality to attach the quoted message to the new reply | 3 | Med | Med | Andy | 21/03/2025 | Yes | 3
134 | TSK-057 Ensure quoted messages display properly in the chat UI | Ensure quoted messages display properly in the chat UI | 3 | Med | Med | Andy | 21/03/2025 | Yes | 3
135 | TSK-058 Store reply relationships in the database for proper retrieval | Store reply relationships in the database for proper retrieval | 2 | Med | High | Vanessa | 21/03/2025 | Yes | 3