## Shadi Marzouk
Member Name |  | ID | Role
Shadi Marzouk |  | 27231466 | Frontend
Log
Date | Task Description |  |  | Issue | Time Spent (H)
2025-10-03 | Completed meeting minutes |  |  |  | 0.75
15/03/2025 | Completed meeting minutes |  |  |  | 0.75
17/03/2025 | Completed meeting minutes |  |  |  | 0.75
14/03/2025 | Add a list of registered users on the dashboard |  |  | TSK-047 | 5
15/03/2025 | Added status filter functionality for users list |  |  | TSK-062 | 2
2025-12-03 | Reorganized team logbook to include issue # |  |  |  | 0.25

## Andy Honla
Member Name |  | ID | Role
Andy Gabriel Ordy Honla |  | 40294997 | Frontend
Log
Date | Task Description |  |  | Issue | Time Spent (H)
2025-09-03 | Ensure quoted messages display properly in the chat UI |  |  | TSK-57 | 3
2025-09-03 | Implement functionality to attach the quoted message to the new reply |  |  | TSK-56 | 3
2025-10-03 | Add a "Reply" button to each message |  |  | TSK-55 | 1
2025-10-03 | Add an emoji picker to the message input field |  |  | TSK-53 | 0.5
2025-12-03 | Ensure emojis appear properly in the chat interface |  |  | TSK-63 | 3

## Scott Svendsen
Member Name |  | ID | Role
Scott Svendsen |  | 40285854 | Frontend
Log
Date | Task Description |  |  | Issue | Time Spent (H)
14/03/2025 | Worked on status options dropdown for profile |  |  | TSK-049 | 2
17/03/2025 | Finished status options in profile modal |  |  | TSK-049 | 0.25
18/03/2025 | Connected the status options to the user list |  |  | TSK-048 | 1.5
21/03/2025 | Added placeholder timestamp on user list |  |  | TSK-048 | 1.5

## Kalin Milanov
Member Name |  | ID | Role
Kalin Milanov |  | 40179417 | Backend
Log
Date | Task Description |  |  | Issue | Time Spent (H)
15/03/2025 | Add a private channel creation button for users |  |  | TSK-042 | 0.5
15/03/2025 | Create an invite pop-up |  |  | TSK-043 | 1
16/03/2025 | Send invitation to users via direct messaging |  |  | TSK-044 | 5
16/03/2025 | Add users to the channel's database |  |  | TSK-045 | 2
16/03/2025 | Make channel messages visible to channel members only |  |  | TSK-046 | 1.5
20/03/2025 | Add status attribute the member's database |  |  | TSK-050 | 0.1
22/03/2025 | Fixed created channels shown as undefined |  |  | TSK-043 | 1
23/03/2025 | Fixed missing red color on "dnd" status |  |  | TSK-048 | 0.1
23/03/2025 | Fixed time zone offset for last seen time |  |  | TSK-051 | 1.5

## Vanessa Cherbaka
Member Name |  | ID | Role
Vanessa Cherbaka |  | 40209927 | Backend
Log
Date | Task Description |  |  | Issue | Time Spent (H)
17/03/2025 | Added a button with a popup form to send channel owners a direct message request to join channels and configured the backend |  |  | TSK-059 | 3
17/03/2025 | Helped fix issues where the invitation could be accepted/ declined multiple times |  |  | TSK-044 | 2.5
18/03/2025 | Added a button with a popup form for users to be able to leave a private channel |  |  | TSK-048 | 1
18/03/2025 | Backend to remove users from private channels |  |  | TSK-049 | 1.5
19/03/205 | Added functionality for last seen timestamps |  |  | TSK-051 | 2
20/03/2025 | Did the backend end for users list |  |  | TSK-047 | 1.5
21/03/2025 | backend for user status |  |  | TSK-050 | 2
21/03/2025 | Direct messaging while offline |  |  | TSK-052 | 1.5

## Weitao Zhang
Member Name |  | ID | Role
Weitao Zhang |  | 40108970 | Backend
Log
Date | Task Description |  |  | Issue | Time Spent (H)
2025-07-03 | Ubuntu tutorial |  |  | Ci | 2
14/3/2025 | Docker and linux command tutorial |  |  | Cd | 2
21/3/2025 | Spilt repository and write trigger judgement |  |  | Cd | 3