## Shadi Marzouk
Member Name |  | ID | Role
Shadi Marzouk |  | 27231466 | Frontend
Log
Date | Task Description |  |  | Time Spent (H)
17/02/2025 | Discussed redesigning UI to a more minimalistic design |  |  | 0.5
18/02/2025 | Redid the UI design for the site |  |  | 8
24/02/2025 | Worked on the chat box for Admins, Users and Channels |  |  | 3
26/02/2025 | Added 'add' functionality to teams and channels |  |  | 2
30/02/2025 | Added 'delete' functionality for channels and teams |  |  | 1
2025-01-02 | Refactored app files for better organization and visibility |  |  | 0.5

## Andy Honla
Member Name |  | ID | Role
Andy Gabriel Ordy Honla |  | 40294997 | Frontend
Log
Date | Task Description |  |  | Time Spent (H)
17/02/2025 | Implementation of message feature posting for both admins and users |  |  | 4
18/02/2025 | Styling of messages in the UI for both users and admins |  |  | 1.5
20/02/2025 | Implementation of message deletion from UI for admins |  |  | 2
24/02/2025 | creation of user addition button |  |  | 0.5
24/02/2025 | Fixing of bugs related to direct messaging and channels pages |  |  | 2.5

## Scott Svendsen
Member Name |  | ID | Role
Scott Svendsen |  | 40285854 | Frontend
Log
Date | Task Description |  |  | Time Spent (H)
2025-02-18 | channel user list and add user to channel button |  |  | 3

## Kalin Milanov
Member Name |  | ID | Role
Kalin Milanov |  | 40179417 | Backend
Log
Date | Task Description |  |  | Time Spent (H)
27/2/2025 | Implement backend for sending private messages |  |  | 2
27/2/2025 | Implement backend for receiving private messages |  |  | 1.5
2025-05-03 | Store private messages with relevant information |  |  | 1
2025-05-03 | Restrict messages to participants only |  |  | 1.5

## Vanessa Cherbaka
Member Name |  | ID | Role
Vanessa Cherbaka |  | 40209927 | Backend
Log
Date | Task Description |  |  | Time Spent (H)
2025-02-26 | Added the popup form to add users to channels and back end to show only users in the option list |  |  | 2
2025-02-27 | Implemented the backend to display the channels for admins |  |  | 1.5
2025-03-01 | implemented socket. IO for messaging |  |  | 2
2025-03-01 | implemented back end to store and display messaging in the channels |  |  | 3
2025-03-02 | implemented backend for deleting messages |  |  | 1
2025-03-07 | fixed errors with direct messaging |  |  | 2

## Weitao Zhang
Member Name |  | ID | Role
Weitao Zhang |  | 40108970 | Backend
Log
Date | Task Description |  |  | Time Spent (H)
2025.2.22 | Fixing compiler issues |  |  | 1
2025.3.7 | Fixing mysql connection issues |  |  | 2
20253.7 | Implement security measures |  |  | 2